## HamB
Chartwell Website | [5 empty] | WO
| Select Customer Plan: | Plan-3
[6 empty] | Hours | Price
Homepage redesign and new website structure |  | Hours | Billing Code | Rate | Price | 30 | 3750
| Create staging pages |  | Project Manager | 125 | 0
| - Copy 12 pages from Government | 3 | Project Manager | 125 | 375
| - Create ~2 new pages for new Services | 0.5 | Project Manager | 125 | 62.5
| Create photoshop design for homepage | 6 | Web Software Engineer | 125 | 750
| Build out new pages (Assumes Final Copy provided) | 0 | Software Engineer | 125 | 0
| - 6 new Services pages | 4.5 | Project Manager | 125 | 562.5
| - Edit new Homepage and Service Landing Page | 1.5 | Project Manager | 125 | 187.5
| New homepage implementation | 12 | Software Engineer | 125 | 1500
| Go-Live |  | Software Engineer | 125 | 0
| - GoLive Checklist | 1.5 | Software Engineer | 125 | 187.5
| - Permalinks | 1 | Software Engineer | 125 | 125
|  |  | Software Engineer | 125 | 0
|  |  | Software Engineer | 125 | 0
|  |  | Software Engineer | 125 | 0
|  | Hours | Billing Code | Rate | Price | 0 | 0
|  |  | Software Engineer | 125 | 0
|  |  | Software Engineer | 125 | 0
|  |  | Software Engineer | 125 | 0
|  |  | Software Engineer | 125 | 0
|  |  | Software Engineer | 125 | 0
|  |  | Software Engineer | 125 | 0
|  |  | Software Engineer | 125 | 0
|  |  | Software Engineer | 125 | 0
|  |  | Software Engineer | 125 | 0
|  |  | Software Engineer | 125 | 0
|  |  | Software Engineer | 125 | 0
|  |  | Software Engineer | 125 | 0
|  |  | Software Engineer | 125 | 0
|  |  | Software Engineer | 125 | 0
|  |  | Software Engineer | 125 | 0
|  |  | Software Engineer | 125 | 0
|  | Hours | Billing Code | Rate | Price | 0 | 0
|  |  | Software Engineer | 125 | 0
|  |  | Software Engineer | 125 | 0
|  |  | Software Engineer | 125 | 0
|  |  | Software Engineer | 125 | 0
|  |  | Software Engineer | 125 | 0
|  |  | Software Engineer | 125 | 0
|  |  | Software Engineer | 125 | 0
|  |  | Software Engineer | 125 | 0
|  | Hours | Billing Code | Rate | Price | 0 | 0
|  |  | Software Engineer | 125 | 0
|  |  | Software Engineer | 125 | 0
|  |  | Software Engineer | 125 | 0
|  |  | Software Engineer | 125 | 0
|  | Hours | Billing Code | Rate | Price | 0 | 0
|  |  | Software Engineer | 125 | 0
|  |  | Software Engineer | 125 | 0
|  |  | Software Engineer | 125 | 0
|  |  | Software Engineer | 125 | 0
|  |  | Software Engineer | 125 | 0
|  |  | Software Engineer | 125 | 0
|  |  | Software Engineer | 125 | 0
|  |  | Software Engineer | 90 | 0
|  | Hours | Billing Code | Rate | Price | 0 | 0
|  |  | Software Engineer | 125 | 0
|  |  | Software Engineer | 125 | 0
|  |  | Software Engineer | 125 | 0
|  |  | Software Engineer | 125 | 0
|  |  | Software Engineer | 125 | 0
|  |  | Software Engineer | 125 | 0
|  |  | Software Engineer | 125 | 0
|  |  | Software Engineer | 90 | 0
SUB TOTALS | [5 empty] | 30 | 3750
Project Supporting Items |  | Hours | Billing Code | Rate | Price | 8 | 1000
| Project Management & Oversight | 8 | Software Engineer | 125 | 1000 | 25%
| Technical Lead |  | Software Engineer | 125 | 0 | 15%
| Post Go-Live Support |  | Software Engineer | 125 | 0 | 10%
| Risk and Contingency |  | Software Engineer | 125 | 0 | 10%
126
COST/PRICE SUMMARY | [5 empty] | 38 | 4750 | 140
|  |  | Total Hours/Price |  |  | 38 | 4750 | 154
|  |  | Blended Rate |  |  |  | 125
[5 empty] | Actual $ | Rounded Hrs | Rounded $
|  |  | Payment 1: | 50% | 2375 | 19.2 | 2400
|  |  | Payment 2: | 40% | 1900 | 15.2 | 1900
|  |  | Payment 3: | 10% | 475 | 4 | 500
|  |  | Actual Price: |  | 4750 | 38.4 | 4800
Note on B23: Kirsten: Events 1. What is LC Meetings? Is it one meeting? more than one? - 2. What is presentation proposals? 3. Do webinars show up for everyone, not just logged in users? ( Example: Quartlerly review webinar ) 4. How many years do the Winner archives go back? 5. Does the datasource meeting vary from the LC meeting in terms of content on the page? Contact 1. How does contact work? How many branches of contact are there? Sitemap 1. should Datasource be in about or in membership or in both? Leadership Council 1. Should there be a page for each ? 2. What is the CTA on the landing page?

## HamA
Chartwell Website | [5 empty] | WO
| Select Customer Plan: | Plan-3
[6 empty] | Hours | Price
Homepage redesign and new website structure |  | Hours | Billing Code | Rate | Price | 24 | 3000
| Create staging pages |  | Project Manager | 125 | 0
| - Copy 12 pages from Government | 3 | Project Manager | 125 | 375
| - Create ~2 new pages for new Services | 0.5 | Project Manager | 125 | 62.5
| Create photoshop design for homepage | 6 | Web Software Engineer | 125 | 750
| Build out new pages | 0 | Software Engineer | 125 | 0
| New homepage implementation | 12 | Software Engineer | 125 | 1500
| Go-Live |  | Software Engineer | 125 | 0
| - GoLive Checklist | 1.5 | Software Engineer | 125 | 187.5
| - Permalinks | 1 | Software Engineer | 125 | 125
|  |  | Software Engineer | 125 | 0
|  | Hours | Billing Code | Rate | Price | 0 | 0
|  |  | Software Engineer | 125 | 0
|  |  | Software Engineer | 125 | 0
|  |  | Software Engineer | 125 | 0
|  |  | Software Engineer | 125 | 0
|  |  | Software Engineer | 125 | 0
|  |  | Software Engineer | 125 | 0
|  |  | Software Engineer | 125 | 0
|  |  | Software Engineer | 125 | 0
|  |  | Software Engineer | 125 | 0
|  |  | Software Engineer | 125 | 0
|  |  | Software Engineer | 125 | 0
|  |  | Software Engineer | 125 | 0
|  |  | Software Engineer | 125 | 0
|  |  | Software Engineer | 125 | 0
|  |  | Software Engineer | 125 | 0
|  |  | Software Engineer | 125 | 0
|  | Hours | Billing Code | Rate | Price | 0 | 0
|  |  | Software Engineer | 125 | 0
|  |  | Software Engineer | 125 | 0
|  |  | Software Engineer | 125 | 0
|  |  | Software Engineer | 125 | 0
|  |  | Software Engineer | 125 | 0
|  |  | Software Engineer | 125 | 0
|  |  | Software Engineer | 125 | 0
|  |  | Software Engineer | 125 | 0
|  | Hours | Billing Code | Rate | Price | 0 | 0
|  |  | Software Engineer | 125 | 0
|  |  | Software Engineer | 125 | 0
|  |  | Software Engineer | 125 | 0
|  |  | Software Engineer | 125 | 0
|  | Hours | Billing Code | Rate | Price | 0 | 0
|  |  | Software Engineer | 125 | 0
|  |  | Software Engineer | 125 | 0
|  |  | Software Engineer | 125 | 0
|  |  | Software Engineer | 125 | 0
|  |  | Software Engineer | 125 | 0
|  |  | Software Engineer | 125 | 0
|  |  | Software Engineer | 125 | 0
|  |  | Software Engineer | 90 | 0
|  | Hours | Billing Code | Rate | Price | 0 | 0
|  |  | Software Engineer | 125 | 0
|  |  | Software Engineer | 125 | 0
|  |  | Software Engineer | 125 | 0
|  |  | Software Engineer | 125 | 0
|  |  | Software Engineer | 125 | 0
|  |  | Software Engineer | 125 | 0
|  |  | Software Engineer | 125 | 0
|  |  | Software Engineer | 90 | 0
SUB TOTALS | [5 empty] | 24 | 3000
Project Supporting Items |  | Hours | Billing Code | Rate | Price | 6 | 750
| Project Management & Oversight | 6 | Software Engineer | 125 | 750 | 25%
| Technical Lead |  | Software Engineer | 125 | 0 | 15%
| Post Go-Live Support |  | Software Engineer | 125 | 0 | 10%
| Risk and Contingency |  | Software Engineer | 125 | 0 | 10%
126
COST/PRICE SUMMARY | [5 empty] | 30 | 3750 | 140
|  |  | Total Hours/Price |  |  | 30 | 3750 | 154
|  |  | Blended Rate |  |  |  | 125
[5 empty] | Actual $ | Rounded Hrs | Rounded $
|  |  | Payment 1: | 50% | 1875 | 15.2 | 1900
|  |  | Payment 2: | 40% | 1500 | 12 | 1500
|  |  | Payment 3: | 10% | 375 | 3.2 | 400
|  |  | Actual Price: |  | 3750 | 30.4 | 3800
Note on B19: Kirsten: Events 1. What is LC Meetings? Is it one meeting? more than one? - 2. What is presentation proposals? 3. Do webinars show up for everyone, not just logged in users? ( Example: Quartlerly review webinar ) 4. How many years do the Winner archives go back? 5. Does the datasource meeting vary from the LC meeting in terms of content on the page? Contact 1. How does contact work? How many branches of contact are there? Sitemap 1. should Datasource be in about or in membership or in both? Leadership Council 1. Should there be a page for each ? 2. What is the CTA on the landing page?

## RateTable
BillCodes | Plan
*NA | AdHoc
DBA | Plan-1
IT Network Engineer | Plan-2
IT Support - Engineer | Plan-3
Project Manager | *
Software Engineer
Solution Architect
SP Software Engineer
SP Support Specialist
Support Specialist
Web Software Engineer
Web Support Specialist
Lookup Table | Std Rate
*Engineeering | 0
*NA.AdHoc | 0
*NA.Plan-1 | 0
*NA.Plan-2 | 0
*NA.Plan-3 | 0
*SharePoint | 0
*Tech Services | 0
*Web | 0
DBA.AdHoc | 225
DBA.Plan-1 | 195
DBA.Plan-2 | 165
DBA.Plan-3 | 150
IT Network Engineer.AdHoc | 145
IT Network Engineer.Plan-1 | 145
IT Network Engineer.Plan-2 | 145
IT Network Engineer.Plan-3 | 145
IT Support - Engineer.AdHoc | 195
IT Support - Engineer.Plan-1 | 95
IT Support - Engineer.Plan-2 | 95
IT Support - Engineer.Plan-3 | 95
Project Manager.Plan-1 | 180
Project Manager.Plan-2 | 165
Project Manager.Plan-3 | 125
Software Engineer.AdHoc | 175
Software Engineer.Plan-1 | 150
Software Engineer.Plan-2 | 145
Software Engineer.Plan-3 | 125
Solution Architect.AdHoc | 225
Solution Architect.Plan-1 | 195
Solution Architect.Plan-2 | 165
Solution Architect.Plan-3 | 150
SP Software Engineer.AdHoc | 175
SP Software Engineer.Plan-1 | 150
SP Software Engineer.Plan-2 | 145
SP Software Engineer.Plan-3 | 125
SP Support Specialist.AdHoc | 175
SP Support Specialist.Plan-1 | 150
SP Support Specialist.Plan-2 | 145
SP Support Specialist.Plan-3 | 125
Support Specialist.AdHoc | 150
Support Specialist.Plan-1 | 125
Support Specialist.Plan-2 | 117
Support Specialist.Plan-3 | 110
Web Software Engineer.AdHoc | 165
Web Software Engineer.Plan-1 | 135
Web Software Engineer.Plan-2 | 125
Web Software Engineer.Plan-3 | 125
Web Support Specialist.AdHoc | 150
Web Support Specialist.Plan-1 | 125
Web Support Specialist.Plan-2 | 117
Web Support Specialist.Plan-3 | 110